## Defect Log
Defect ID | Date Found | Module | Severity | Priority | Summary | Steps to Reproduce | Expected Result | Actual Result | Status | Found By | Assigned To | Fixed In | Verified By | Date Closed
DEF-001 | 2026-05-08 | Profile | High | P1 | Profile photo not displaying after upload | 1. Login as member 2. Edit profile 3. Upload JPEG avatar 4. Save and view dashboard | Avatar visible on profile and dashboard | Broken image icon; 404 on avatar URL | Closed | Apas, Christel Grace | Zerrudo, Jase Karl | v1.0.0-build3 | Apas, Christel Grace | 2026-05-09
DEF-002 | 2026-05-07 | Activities | Medium | P2 | Pedometer requires device sensors; fails on desktop | 1. Open Dashboard on desktop 2. Click Start pedometer | Steps trackable on all platforms | Error: device motion not available | Closed | Tuazon, John Rae | Zerrudo, Jase Karl | v1.0.0-build4 | Tuazon, John Rae | 2026-05-08
DEF-003 | 2026-05-09 | UI/UX | Medium | P2 | Form inputs white-on-white on Goals, Train, Stats pages | 1. Open Goals 2. Click New goal 3. Observe input fields | Dark theme inputs with readable text | White background, white text invisible | Closed | Labe, Sherwin | Zerrudo, Jase Karl | v1.0.0-build5 | Apas, Christel Grace | 2026-05-10
DEF-004 | 2026-05-09 | Admin | Medium | P2 | Admin user detail missing daily target progress | 1. Login as admin 2. Expand member card | Show steps/calories/workouts targets and today progress | Only basic profile info shown | Closed | Labe, Sherwin | Zerrudo, Jase Karl | v1.0.0-build6 | Labe, Sherwin | 2026-05-10
DEF-005 | 2026-05-14 | Analytics | Low | P4 | Chart legend text small on mobile viewport | 1. Open Stats on 375px width 2. View chart legend | Legend readable without zoom | Legend text 10px, hard to read | Open | Apas, Christel Grace | Zerrudo, Jase Karl | — | — | —
DEF-006 | 2026-05-14 | Goals | Low | P4 | No confirmation before deleting goal | 1. Goals page 2. Click delete on goal | Confirm dialog before delete | Goal deleted immediately | Open | Tuazon, John Rae | Zerrudo, Jase Karl | — | — | —
DEF-007 | 2026-05-06 | Auth | Low | P3 | Password field shows no strength indicator | 1. Register new user 2. Enter weak password | Optional strength hint | No indicator (acceptable for MVP) | Closed | Apas, Christel Grace | — | N/A — accepted | Tuazon, John Rae | 2026-05-07
DEF-008 | 2026-05-10 | Backend | Medium | P2 | Schema migration error on fresh DB without user_profiles table | 1. Delete DB 2. Start backend | Clean migration on empty DB | OperationalError on migrate_schema | Closed | Zerrudo, Jase Karl | Zerrudo, Jase Karl | v1.0.0-build2 | Zerrudo, Jase Karl | 2026-05-10