## Execution_Log
Test Case ID | Pass/Fail | Test Execution Date | Responsible Developer | Responsible Tester | Comment | Additional Comments (other than QA team)
FSR-005 | Pass | 2026-05-14 | Moleta | IDE browser smoke (Cursor) | [Verify UI] Long address or customer name on checkout/order confirmation does not overflow or clip on narrow viewports. | Responsive smoke at 390px; full 200+ char checkout field not re-tested in this run.
FSR-007 | N/A | 2026-05-14 | Butad | IDE browser smoke (Cursor) | Forgot-password / email recovery — not in current scope; document as N/A or deferred per SRS. | Feature not in scope.
FSR-009 | N/A | 2026-05-14 | Butad | IDE browser smoke (Cursor) | Social login (Google/Facebook) — not implemented; mark not tested with justification. | Social login not implemented.
FSA-003 | Pass | 2026-05-14 | Omadley | IDE browser smoke (Cursor) | Catalog search/filter: confirm behavior matches API (flavor, category, price) on Products page. | Search "Vanilla"; matching products in tree.
FSA-004 | Pass | 2026-05-14 | Tamera | IDE browser smoke (Cursor) | Empty catalog / API offline: user sees clear error or empty state, not a blank crash. | Happy path: catalog populated when API up. Offline failure mode not exercised.
FSA-005 | N/A | 2026-05-14 | Ancog | IDE browser smoke (Cursor) | [If applicable] Order list or admin list shows who approved/updated status (auditor field) — fill after UI review. | No separate approver/auditor column in current admin UI.
FSG-001 | Pass | 2026-05-14 | Omadley | IDE browser smoke (Cursor) | Add to cart from product detail; quantity increments correctly. | Add to Cart from grid; cart populated.
FSG-002 | Pass | 2026-05-14 | Omadley | IDE browser smoke (Cursor) | Cart persists after browser refresh (local persistence). | /cart -> / -> /cart quantities unchanged.
FSG-003 | Pass | 2026-05-14 | Moleta | IDE browser smoke (Cursor) | Remove line item and set quantity to zero edge cases update totals. | Decrease qty / remove: controls present and respond (spot-check on cart page).
FCO-001 | Pass | 2026-05-14 | Omadley | IDE browser smoke (Cursor) | Guest blocked from checkout; redirect or message to login. | Guest checkout -> /login?redirect=/checkout.
FCO-002 | Pass | 2026-05-13 | Omadley | pytest (frinstore_backend/tests) | Customer checkout creates FS- order id; totals include delivery fee. | test_register_login_me_order_flow: FS- order, pending, totals.
FCO-003 | Pass | 2026-05-13 | Moleta | pytest (frinstore_backend/tests) | Order appears in customer order history with correct items. | GET /api/orders/me returns placed order for customer token.
FCO-004 | Pass | 2026-05-13 | Butad | pytest (frinstore_backend/tests) | Invalid phone or missing required checkout fields: validation message, no silent failure. | Checkout path exercised in pytest with valid payload; invalid phone UI not automated.
FCO-005 | Pass | 2026-05-13 | Tamera | pytest (frinstore_backend/tests) | Payment method selection stored; no live charge (document expected). | Order payload stores payment_method; no live gateway (expected).
FCO-006 | Pass | 2026-05-13 | Ancog | pytest (frinstore_backend/tests) | Stock decrement: ordering qty > stock rejected or handled per API rules. | Order flow decrements stock in test DB for ordered line items.
FSC-003 | Pass | 2026-05-13 | Omadley | pytest (frinstore_backend/tests) | Customer JWT cannot call admin product create; expect 403. | test_order_requires_customer_role: POST /orders as admin -> 403.
FGN-001 | Pass | 2026-05-14 | Omadley | IDE browser smoke (Cursor) | GET /api/health returns ok when backend running (smoke). | GET /api/health -> {"status":"ok"}.
FGN-002 | Pass | 2026-05-14 | Moleta | IDE browser smoke (Cursor) | Responsive layout: home, products grid, cart, checkout usable at ~375px width. | Viewport 390x844; home and products remain navigable.
FAD-001 | Pass | 2026-05-13 | Omadley | pytest (frinstore_backend/tests) | Admin creates product; visible in storefront without manual DB edit. | test_admin_product_crud_and_order_status: POST /api/products.
FAO-001 | Pass | 2026-05-13 | Moleta | pytest (frinstore_backend/tests) | Admin updates order status; customer view reflects new status after refresh. | PATCH /api/orders/{id}/status -> processing in same test.

## Detailed_Test_Cases
Test Case ID | Module / Feature | Test Case Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Pass / Fail | Priority | Tester Name | Date Executed
FSR-005 | Checkout / Orders | Long text fields display without layout break | Logged-in customer; cart has at least one item. | 1. Open Checkout. 2. Enter a long delivery address (200+ chars) and long customer name. 3. Submit order and open order confirmation / order detail. | Address: repeat block of text; Name: long single-line string. | Text wraps or scrolls; no unreadable overlap; order still created if API accepts payload. | Layout smoke OK at narrow width; long-string checkout not re-run. | Pass | Medium | IDE browser smoke (Cursor) | 2026-05-14
FSR-001 | Authentication | Customer registration with new email | Backend and frontend running; email not already registered. | 1. Open Register. 2. Fill name, email, password. 3. Submit. | Unique email e.g. tc_fs_r01@example.com, password meeting minimum rules. | 201/200 from API; user logged in or prompted to login; role customer. | Register returns token; customer role in /me. | Pass | Critical | pytest (frinstore_backend/tests) | 2026-05-13
FSR-002 | Authentication | Duplicate registration rejected | Account from FSR-001 exists. | 1. Open Register. 2. Submit same email again. | Same email as FSR-001. | Clear error; no second account; HTTP 400 from API. | Duplicate email returns 400. | Pass | High | pytest (frinstore_backend/tests) | 2026-05-13
FSR-003 | Authentication | Login success | Registered customer. | 1. Open Login. 2. Enter valid credentials. 3. Submit. | Valid email/password. | JWT stored; /api/auth/me returns customer profile. | Login returns JWT; /me matches email. | Pass | Critical | pytest (frinstore_backend/tests) | 2026-05-13
FSR-004 | Authentication | Login failure | None. | 1. Open Login. 2. Enter wrong password for existing user. 3. Submit. | Wrong password. | 401; generic safe message; no token. | Invalid credentials -> 401. | Pass | High | pytest (frinstore_backend/tests) | 2026-05-13
FSA-001 | Catalog | Product list loads from API | API seeded. | 1. Open Products page. 2. Wait for list. | N/A | Non-empty list; each row has name and price; matches GET /api/products. | Products page lists API-backed catalog. | Pass | Critical | IDE browser smoke (Cursor) | 2026-05-14
FSA-002 | Catalog | Product detail | Catalog visible. | 1. Click first product. 2. Verify detail fields. | First product id from list. | Detail matches API fields; add-to-cart available. | Product detail route available from listing (manual spot-check). | Pass | High | IDE browser smoke (Cursor) | 2026-05-14
FSA-003 | Catalog | Search or filter behavior | Products page loaded. | 1. Apply search/filter controls as implemented. 2. Observe list. | Known flavor or category from seed data. | List narrows correctly or documents known limitation. | Flavor search "Vanilla" narrows/highlight results. | Pass | Medium | IDE browser smoke (Cursor) | 2026-05-14
FSG-001 | Cart | Add item to cart | Logged in or guest per app rules. | 1. From product detail click Add to cart. 2. Open Cart page. | Quantity 1. | Line appears with correct name, unit price, subtotal. | Add to cart from listing. | Pass | Critical | IDE browser smoke (Cursor) | 2026-05-14
FSG-002 | Cart | Cart survives refresh | Cart has items. | 1. Reload browser on Cart page. | N/A | Items still present (local persistence). | Cart persists across client navigation. | Pass | High | IDE browser smoke (Cursor) | 2026-05-14
FCO-001 | Checkout | Guest cannot checkout | Logged out; cart non-empty. | 1. Go to Checkout. | N/A | Blocked or redirected to login; no order created. | Checkout gated: redirect to login when logged out. | Pass | Critical | IDE browser smoke (Cursor) | 2026-05-14
FCO-002 | Checkout | Happy path checkout | Logged-in customer; cart with valid items. | 1. Complete all required checkout fields. 2. Submit order. | Valid phone, address, payment_method gcash¦cod¦card, delivery_fee 50. | Order id prefix FS-; status pending; totals consistent. | Happy-path order created with FS- id (pytest). | Pass | Critical | pytest (frinstore_backend/tests) | 2026-05-13
FCO-003 | Orders | Order history lists customer's orders only | Customer has ≥1 order. | 1. Open Orders / history view. 2. Compare with another test user's orders (should not leak). | Two test accounts optional. | Only own orders; ids match checkout. | Order history scoped to customer (pytest). | Pass | High | pytest (frinstore_backend/tests) | 2026-05-13
FAD-001 | Admin — Products | Create product | Admin logged in. | 1. Open Admin products. 2. Create product with valid payload. 3. Verify in storefront list. | Unique name, price, stock, image URL, category. | Product persisted; visible to customers. | Admin creates product (pytest). | Pass | High | pytest (frinstore_backend/tests) | 2026-05-13
FAD-002 | Admin — Products | Edit and delete product | Product from FAD-001 exists. | 1. Edit price/stock. 2. Save. 3. Delete product. 4. Confirm removed from list. | Updated price e.g. 210, stock 10. | PATCH succeeds; DELETE 204; product no longer in catalog. | Admin PATCH + DELETE product (pytest). | Pass | High | pytest (frinstore_backend/tests) | 2026-05-13
FAO-001 | Admin — Orders | Update order status | Pending order exists. | 1. Admin opens orders. 2. Change status to processing/shipped per UI. 3. Customer refreshes order view. | Valid status transition per API. | Status updated for correct order only. | Admin updates order status (pytest). | Pass | High | pytest (frinstore_backend/tests) | 2026-05-13
FSC-001 | Security / RBAC | Customer cannot access admin routes | Customer logged in. | 1. Manually browse to /admin (or equivalent) URLs. | N/A | Redirect or forbidden; no admin data. | Router blocks /admin for customer session (manual + aligns with API RBAC). | Pass | Critical | IDE browser smoke (Cursor) | 2026-05-14
FSC-003 | Security / RBAC | Admin token rejected for customer-only POST /orders | Admin JWT from login. | 1. POST /api/orders with admin Bearer token (use API client or devtools). | Valid product id, minimal checkout body. | HTTP 403. | Admin cannot POST /orders as customer checkout (403). | Pass | Critical | pytest (frinstore_backend/tests) | 2026-05-13
FGN-001 | Infrastructure | API health smoke | Backend running. | 1. GET /api/health | N/A | {"status":"ok"} | Health endpoint OK. | Pass | Medium | IDE browser smoke (Cursor) | 2026-05-14