## Defect_Log
Defect ID | Title | Module / Feature | Severity | Priority | Phase Found | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Date Reported | Date Resolved
DEF-001 | Long checkout address overflows on narrow screen | Checkout UI | Medium | P2 | System | 1. Login as customer with item in cart. 2. Open checkout. 3. Paste 250+ character address string. 4. Submit and view confirmation on ~375px width. | Text wraps within card without horizontal clipping. | Horizontal scroll or clipped text observed. | Open | Tamera | 2026-05-13
DEF-002 | Catalog filter does not reset when clearing search box | Products / catalog | Low | P3 | System | 1. Open Products. 2. Type a filter string that narrows list. 3. Clear text field with backspace fully. | Full catalog (or default state) returns. | List remains filtered until manual refresh. | In Progress | Tamera | 2026-05-13
DEF-003 | Missing phone validation message on checkout | Checkout validation | Medium | P1 | System | 1. Proceed to checkout with invalid phone (too short). 2. Submit. | Inline validation explains required phone format. | Generic error or API error surfaced without field hint. | Resolved | Tamera | 2026-05-12 | 2026-05-13
DEF-004 | Broken image URL shows oversized placeholder | Admin product form / catalog card | Low | P3 | System | 1. Admin creates product with invalid image URL. 2. View storefront card. | Graceful broken-image icon within layout bounds. | Placeholder stretches layout. | Deferred | Tamera | 2026-05-11
DEF-005 | Admin order status list sorts confusingly by default | Admin orders | Low | P3 | UAT | 1. Create multiple orders. 2. Open admin orders view. | Newest pending orders appear at top. | Tester perceived wrong default ordering. | Open | Tamera | 2026-05-13
DEF-006 | Brief flash of admin route before redirect for customer | Security / routing | High | P1 | UAT | 1. Login as customer. 2. Manually navigate to admin URL. 3. Observe first paint. | Immediate guard without sensitive layout flash. | Momentary layout visible before redirect. | Retested | Tamera | 2026-05-12 | 2026-05-13
DEF-007 | Cart footer overlaps checkout button on small height viewport | Cart / responsive | Medium | P2 | System | 1. Add multiple items. 2. Open cart on short laptop window height. | CTA remains reachable (scrollable region). | Overlap makes checkout hard to tap. | Resolved | Tamera | 2026-05-12 | 2026-05-13
DEF-008 | Delivery fee not reflected in displayed total until refresh | Checkout totals | Critical | P0 | System | 1. Add item, open checkout. 2. Change delivery fee field if editable, or trigger recalculation path per UI. 3. Observe total before submit. | Displayed total always matches server calculation. | Stale total until manual refresh (illustrative — verify against your build). | Closed | Tamera | 2026-05-11 | 2026-05-12